## Launch Timeline
Launch Timeline & Milestone Tracker
Phase | Task/Milestone | Start Date | End Date | Duration | Status | Owner | Dependencies | Notes
Pre-Launch Preparation
| Finalize pricing strategy | 2025-07-25 | 1900-01-02 | 3 days | Not Started | CEO | Market research complete | Use pricing calculator
| Complete website optimization | 0 | 2025-07-30 | 5 days | Not Started | Marketing | Content ready | SEO and mobile optimization
| Prepare marketing materials | 1900-01-02 | 1900-01-06 | 7 days | Not Started | Marketing | Brand guidelines | Brochures, presentations
| Set up analytics tracking | 0 | 1900-01-04 | 2 days | Not Started | Tech Lead | Website complete | Google Analytics, etc.
| Train team on processes | 1900-01-06 | 1900-01-02 | 3 days | Not Started | Operations | SOPs documented | Customer service training
MILESTONE: Pre-Launch Complete |  | 2025-07-30
Soft Launch Phase
| Identify early adopters | 1900-01-02 | 1900-01-04 | 5 days | Not Started | Sales | Target list ready | 10-15 prospects
| Launch to early adopters | 0 | 1900-01-16 | 14 days | Not Started | Sales | Early adopters identified | Personal outreach
| Collect initial feedback | 1900-01-02 | 1900-01-20 | 21 days | Not Started | Customer Success | Customers onboarded | Weekly check-ins
| Optimize based on feedback | 1900-01-16 | 1900-01-09 | 7 days | Not Started | Operations | Feedback collected | Process improvements
MILESTONE: Soft Launch Complete |  | 1900-01-20
Full Launch Phase
| Launch marketing campaigns | 1900-01-09 | 1899-12-31 | 1 day | Not Started | Marketing | Materials ready | Multi-channel launch
| Press release distribution | 0 | 1900-01-10 | 1 day | Not Started | PR | Press kit ready | Industry publications
| Social media campaign | 0 | 1900-01-29 | 30 days | Not Started | Marketing | Content calendar | Daily posting schedule
| Email marketing launch | 0 | 1900-01-29 | 30 days | Not Started | Marketing | Email list ready | Welcome series
| Networking events | 0 | 1900-02-28 | 60 days | Not Started | Sales | Event calendar | Industry conferences
MILESTONE: Full Launch Complete |  | 1900-01-29
Post-Launch Optimization
| Analyze launch metrics | 1900-02-28 | 1900-01-06 | 7 days | Not Started | Analytics | Data collected | Performance review
| Customer feedback analysis | 0 | 1900-03-05 | 5 days | Not Started | Customer Success | Feedback systems active | Satisfaction surveys
| Process optimization | 1900-01-06 | 1900-01-13 | 14 days | Not Started | Operations | Analysis complete | Efficiency improvements
| Scale successful channels | 1900-03-05 | 1900-02-05 | 30 days | Not Started | Marketing | Channel performance data | Budget reallocation
MILESTONE: Launch Optimization Complete |  | 1900-03-05
Formulas:
End Date = [Start Date, row above]+3

## Milestone Summary
Launch Milestone Summary
Milestone | Target Date | Actual Date | Status | Key Deliverables
Pre-Launch Complete | 0 |  | Pending | All systems ready, team trained
Soft Launch Complete | 0 |  | Pending | Early adopters engaged, feedback collected
Full Launch Complete | 0 |  | Pending | All channels active, market aware
Launch Optimization Complete | 0 |  | Pending | Processes optimized, scaling ready